## Estimate Summary
PAINTING ESTIMATE
Food Lion Store #0387 Remodel — Troy, NC
1020 Albemarle Road, Troy, NC 27371
Bid Date: March 18, 2026 at 2:00 PM ¦ Prepared by: Carolina Commercial Finishes
Date Prepared: March 17, 2026 — SOW-VALIDATED ESTIMATE
SCOPE CATEGORY | LABOR HRS | LABOR $ | MATERIALS $ | DIRECT COST | % OF TOTAL
Interior Walls (26 rooms, SOW-adjusted) | 322.1 | 9017.97 | 5866.32 | 14884.29 | 59.3%
Ceilings (Dryfall + GWB + Epoxy) | 45 | 1260 | 336.29 | 1596.29 | 6.4%
Doors & Frames (28 units) | 41.5 | 1162 | 596 | 1758 | 7.0%
Exterior Painting | 76 | 2128 | 930.65 | 3058.65 | 12.2%
Prep, Misc & Equipment | 90 | 2520 | 1280 | 3800 | 15.1%
DIRECT COST TOTALS | 574.6 | 16087.97 | 9009.26 | 25097.23 | 100%
Direct Cost |  |  |  | 25097.23
Overhead (12%) |  |  |  | 3011.67
Markup (20%) |  |  |  | 5621.78
BID PRICE (PAINTING ONLY) |  |  |  | 33730.68
KEY METRICS
Total Paintable SF (SOW-adjusted): | 30125
Takeoff Total SF (before SOW adjustment): | 40099
Blended Rate ($/SF): | 1.12
Total Labor Hours: | 575
Estimated Duration (2-man crew): | 36 days
Estimated Duration (3-man crew): | 24 days
Labor Rate (burdened): | $28.00/hr
EXCLUSIONS
• Wallcovering / decorative wall systems (Section 09 77 00)
• Electrostatic painting
• Floor painting / traffic markings
• Vestibule walls (aluminum/glass — GC scope)
• Marlite installation and finishing (GC scope)
• Ceramic/quarry tile areas (tile contractor scope)
• Cooler/freezer panel surfaces
• Acoustical ceiling tile replacement or cleaning
• Aluminum soffit cleaning (GC scope)
• Standing seam metal roof painting
• Pressure washing (GC scope)
• Asbestos abatement
NOTES
• All paint from Sherwin-Williams ONLY — National Account 'National Parent #C137'
• Sales area painting is NIGHT WORK ONLY (10 PM - 8 AM)
• Restroom & janitor ceiling paint AFTER new light fixtures installed
• Active operating store — all work coordinated with store manager
• Interior wall SF adjusted per SOW (see Interior Walls tab for breakdown)
• Exposed ceiling rated at 125 SF/hr (structure spray, not flat ceiling)

## Interior Walls
INTERIOR WALLS — SOW-VALIDATED BREAKDOWN
Room # | Room Name | Takeoff SF | SOW % | Paint SF | Method | Coats | Paint System | Labor Hrs | Labor $ | Material $ | Total $ | Night
100 | Sales Area | 8045.61 | 100% | 8045.61 | Spray | P+2 | ProBlock Primer + ProMar 200 Eg-Shel | 98.3 | 2753.39 | 1528.67 | 4282.05 | Y
102 | Corridor / Back of House | 1460.15 | 100% | 1460.15 | Spray+BR | SP+2 | Pro-Cryl Primer (spot) + Pre-Cat Epoxy Eg-Shel | 15.6 | 436.1 | 394.24 | 830.34
103 | Associate Break Room | 504.38 | 100% | 504.38 | Spray+BR | SP+2 | Pro-Cryl Primer (spot) + Pre-Cat Epoxy Eg-Shel | 5.4 | 150.64 | 136.18 | 286.82
104 | DMO / Associate Restroom | 601.08 | 100% | 601.08 | B&R | BF+2 | Block Filler + Pre-Cat Epoxy Eg-Shel | 15 | 420.76 | 204.37 | 625.12
105 | Meat Prep (exposed block only) | 5147.96 | 30% | 1544.39 | B&R | BF+2 | Kem Cati-Coat Filler + Macropoxy 646 | 38.6 | 1081.07 | 525.09 | 1606.17
106 | Receiving Room (CMU/GWB only) | 14929.56 | 40% | 5971.82 | Spray+BR | SP+2 | Pro-Cryl Primer (spot) + Pre-Cat Epoxy Eg-Shel | 63.7 | 1783.58 | 1612.39 | 3395.97
107 | Janitor | 359.46 | 100% | 359.46 | Spray+BR | SP+2 | Pro-Cryl Primer (spot) + Pre-Cat Epoxy Eg-Shel | 3.8 | 107.36 | 97.05 | 204.41
108 | Deli/Bakery Prep (above tile/Marlite) | 1451.03 | 30% | 435.31 | B&R | BF+2 | Kem Cati-Coat Filler + Macropoxy 646 | 10.9 | 304.72 | 148.01 | 452.72
109 | Produce Prep (exposed CMU only) | 655.86 | 30% | 196.76 | B&R | BF+2 | Kem Cati-Coat Filler + Macropoxy 646 | 4.9 | 137.73 | 66.9 | 204.63
110 | Cash Office | 207.96 | 100% | 207.96 | B&R | SP+2 | ProMar Primer (spot) + Pre-Cat Epoxy Eg-Shel | 3 | 83.18 | 56.15 | 139.33
111 | Men's Restroom | 248.39 | 100% | 248.39 | B&R | BF+2 | Block Filler + Pre-Cat Epoxy Eg-Shel | 6.2 | 173.87 | 84.45 | 258.33
112 | Women's Restroom | 220.78 | 100% | 220.78 | B&R | BF+2 | Block Filler + Pre-Cat Epoxy Eg-Shel | 5.5 | 154.55 | 75.07 | 229.61
113 | Work Room / Outer Office | 281.25 | 100% | 281.25 | B&R | SP+2 | ProMar Primer (spot) + Pre-Cat Epoxy Eg-Shel | 4 | 112.5 | 75.94 | 188.44
114 | Deli/Bakery Sales (GWB above cases) | 1516.17 | 60% | 909.7 | Spray | P+2 | ProBlock Primer + ProMar 200 Eg-Shel | 11.1 | 311.32 | 172.84 | 484.16 | Y
115 | Produce Sales | 611.73 | 100% | 611.73 | Spray | P+2 | ProBlock Primer + ProMar 200 Eg-Shel | 7.5 | 209.35 | 116.23 | 325.58 | Y
116 | Floral | 258.92 | 100% | 258.92 | Spray | P+2 | ProBlock Primer + ProMar 200 Eg-Shel | 3.2 | 88.61 | 49.19 | 137.8 | Y
117 | Meat Sales | 276.94 | 100% | 276.94 | Spray | P+2 | ProBlock Primer + ProMar 200 Eg-Shel | 3.4 | 94.78 | 52.62 | 147.39 | Y
118 | Seafood | 336.92 | 100% | 336.92 | Spray | P+2 | ProBlock Primer + ProMar 200 Eg-Shel | 4.1 | 115.3 | 64.01 | 179.32 | Y
119 | Pharmacy / Health | 371.49 | 100% | 371.49 | Spray | P+2 | ProBlock Primer + ProMar 200 Eg-Shel | 4.5 | 127.13 | 70.58 | 197.72 | Y
120 | Motor Room | 601 | 40% | 240.4 | Spray+BR | SP+2 | Pro-Cryl Primer (spot) + Pre-Cat Epoxy Eg-Shel | 2.6 | 71.8 | 64.91 | 136.71
121 | Mechanical Room | 352.88 | 40% | 141.15 | Spray+BR | SP+2 | Pro-Cryl Primer (spot) + Pre-Cat Epoxy Eg-Shel | 1.5 | 42.16 | 38.11 | 80.27
122 | Electrical Room | 357.61 | 40% | 143.04 | Spray+BR | SP+2 | Pro-Cryl Primer (spot) + Pre-Cat Epoxy Eg-Shel | 1.5 | 42.72 | 38.62 | 81.34
124 | Compressor Room | 269.7 | 40% | 107.88 | Spray+BR | SP+2 | Pro-Cryl Primer (spot) + Pre-Cat Epoxy Eg-Shel | 1.2 | 32.22 | 29.13 | 61.35
125 | Storage / Misc | 333.83 | 100% | 333.83 | Spray+BR | SP+2 | Pro-Cryl Primer (spot) + Pre-Cat Epoxy Eg-Shel | 3.6 | 99.7 | 90.13 | 189.84
126 | IT / Server Room | 243.29 | 40% | 97.32 | Spray+BR | SP+2 | Pro-Cryl Primer (spot) + Pre-Cat Epoxy Eg-Shel | 1 | 29.07 | 26.28 | 55.34
127 | Sprinkler Room | 455.13 | 40% | 182.05 | Spray+BR | SP+2 | Pro-Cryl Primer (spot) + Pre-Cat Epoxy Eg-Shel | 1.9 | 54.37 | 49.15 | 103.53
TOTALS |  | 40099.08 |  | 24088.71 |  |  |  | 322.1 | 9017.97 | 5866.32 | 14884.29
SOW ADJUSTMENT NOTES:
Room 101 (Vestibule) EXCLUDED — walls are aluminum/glass, not painting scope. Doors in Doors sheet.
Room 105 (Meat Prep (exposed block only)): 30% of takeoff — 30% — Marlite/tile/cooler panels by others. Paint exposed CMU + conduit/jboxes
Room 106 (Receiving Room (CMU/GWB only)): 40% of takeoff — 40% — Cooler/freezer panels, dock doors, Marlite excluded
Room 108 (Deli/Bakery Prep (above tile/Marlite)): 30% of takeoff — 30% — Marlite, ceramic tile, SS wraps by others
Room 109 (Produce Prep (exposed CMU only)): 30% of takeoff — 30% — Nudo panels, Marlite, cooler panels by others
Room 114 (Deli/Bakery Sales (GWB above cases)): 60% of takeoff — 60% — Marlite, canopy finishes by others
Room 120 (Motor Room): 40% of takeoff — 40% — Equipment, piping obstruct most walls
Room 121 (Mechanical Room): 40% of takeoff — 40% — Equipment obstructs most walls
Room 122 (Electrical Room): 40% of takeoff — 40% — Panels cover most wall space
Room 124 (Compressor Room): 40% of takeoff — 40% — Refrigeration equipment obstructs
Room 126 (IT / Server Room): 40% of takeoff — 40% — Server racks obstruct most walls
Room 127 (Sprinkler Room): 40% of takeoff — 40% — Riser/piping obstructs walls

## Ceilings
CEILINGS — CORRECTED BREAKDOWN
Area | Ceiling SF | Method | Coats | Paint System | Labor Hrs | Labor $ | Material $ | Total $
Exposed Ceiling - Dryfall (Receiving, BOH) | 2778.94 | Spray (lift) | SP+1 | Pro-Cryl Primer (spot bare/rust) + Dryfall Flat B42W181 | 33.2 | 929.01 | 155.62 | 1084.63
Gypsum Board Ceiling (Offices, Corridors) | 676.48 | Spray | SP+2 | ProMar 200 Primer (spot) + ProMar 200 Eg-Shel | 5.2 | 145.22 | 101.47 | 246.69
Restroom Ceilings (Men's, Women's, DMO) - Epoxy | 250 | Roll | 2 | Pre-Cat Epoxy Eg-Shel SW #7005 Pure White | 5 | 140 | 60 | 200
Janitor Room Ceiling - Epoxy | 80 | Roll | 2 | Pre-Cat Epoxy Eg-Shel | 1.6 | 44.8 | 19.2 | 64
TOTALS | 3785.42 |  |  |  | 45 | 1260 | 336.29 | 1596.29
EXPOSED CEILING RATE NOTES:
• Dryfall spray on open structure (deck/joists/pipes/conduit) @ 125 SF/hr — NOT flat ceiling rate
• Spot prime bare/rusted areas (20% coverage) @ 80 SF/hr from lift
• Setup includes containment, lift positioning, protection of surfaces below
• Spray @ 125 SF/hr = 22.2h + Spot prime 6.9h + Setup 4.0h

## Doors & Frames
DOORS & FRAMES — DETAILED BREAKDOWN
Item | Qty | Labor Hrs | Labor $ | Material $ | Total $
Single Swing HM Doors (2 sides + frame) | 21 | 27.9 | 782.04 | 420 | 1202.04
Double Swing HM Doors (2 sides + frame) | 5 | 9.6 | 270.06 | 146 | 416.06
Automatic Door Packages - clean & repaint (2 sets) | 2 | 4 | 112 | 30 | 142
TOTALS | 28 | 41.5 | 1162 | 596 | 1758
NOTES:
• All HM doors: scuff sand, full prime (Pro-Cryl B66-1310), 2 coats Pre-Cat Epoxy Semi-Gloss K46
• Automatic/sliding doors: clean and repaint (silver doors NOT painted)
• Install new door silencers on all frames AFTER painting (by GC)

## Exterior
EXTERIOR PAINTING — DETAILED BREAKDOWN
Item | SF | Method | Coats | Labor Hrs | Labor $ | Material $ | Total $
Exterior Walls (CMU/EIFS) - Repaint | 2250.68 | Spray+BR | SP+2 | 24 | 672.2 | 490.65 | 1162.85
Front Ext Metals (doors, frames, bollards, lintels, handrails, light bases, access panels) |  | B&R/Spray | SP+2 | 24 | 672 | 180 | 852
Cart Corral - Prime & Paint (SW 7068 Grizzle Gray) |  | Spray | P+2 | 4 | 112 | 45 | 157
Metal Panels Under Windows (DTM Enduring Bronze) |  | B&R | 2 | 3 | 84 | 35 | 119
Alarm Box/Bell Under Canopy + Access Hatches |  | B&R | 2 | 2 | 56 | 20 | 76
EIFS Repaint (after storefront sign removal/skim coat) |  | Spray | 2 | 3 | 84 | 40 | 124
Rear Ext Metals (stairs, canopy supports, guardrail, dock stencil) |  | B&R/Spray | SP+2 | 16 | 448 | 120 | 568
TOTALS |  |  |  | 76 | 2128 | 930.65 | 3058.65

## Prep & Misc
PREP, MISC & EQUIPMENT — DETAILED BREAKDOWN
Item | Labor Hrs | Labor $ | Material $ | Total $
Surface Prep (scrape, sand, patch, caulk - all areas) | 24 | 672 | 120 | 792
Masking & Protection (plastic, tape, paper, drop cloths) | 20 | 560 | 180 | 740
MEP Painting (exposed pipes, conduit, equipment per spec) | 16 | 448 | 80 | 528
Touch-Up & Punch List Allowance | 10 | 280 | 50 | 330
Mobilization / Demobilization (equipment, setup) | 8 | 224 | 0 | 224
Equipment (airless sprayer, scissor lift rental) | 0 | 0 | 850 | 850
Night Work Productivity Allowance (sales area 10PM-8AM) | 12 | 336 | 0 | 336
TOTALS | 90 | 2520 | 1280 | 3800